## Softdev
To do list |  | Assign to | Deadline | Percentage
| Event Table | Project Team | 2017-03-14 | 100%
Diagram
| Context Level Diagram | Gail Haboc | 3/14/2017 or 3/15/2017 | 100%
Data Flow Diagram
By Process
| Use Case Diagram | Kuya Arnold
| Database Diagram | Aira Carpio
| Finalize Data Process | Aira Carpio | 2017-03-14 | 80%
| Datawarehousing Process |  | 2017-03-20
| Data Query of other system |  | 2017-03-17
Documents
Project Proposal
| Definition of System |  | 2017-03-14 | 100%
| Process of System |  | 2017-03-14 | 100%
High-Level Diagram
| Proposed BI Tool | Kuya Arnold | 2017-03-17
| Include Pricing |  | 2017-03-17
| Features(Deployment) |  | 2017-03-17
| User Manual | Project Team
| PROTOTYPE |  | (Every Saturday)
| CLOUD9- MYSQL | Kuya Arnold | 2017-03-11 | 100%
Presentation
Video(AVP)
Prototype
PPT

## Quality
To do list | Assign to | Deadline | Percentage
Quality Assurance
Software Quality Assurance
Error Handling

## Sheet2
1) Kung yung Data ba na kailangan nila makita ay sa Monitoring System or sa System nila..? - kasi pwede namin nilang tignan mismo yung data na kailangan nila sa monitoring system 2) Kung yung requesting ba ay sa system namin or sa kanila -