## Sheet1
Quality Assurance Testing Timeline for <Release x.x>
This timeline document is intended to serve as a alist of tasks needed to be accomplished during the Quality Assurance testing phase for a showing the duration of each task in the format <n> days, the start and finish in the format <nn/dd/yyyy>, the predecessors for the task and resource/s for the task to be successfuly completed.
Task ID | Task Name | Duration | Start | Finish | % Complete | Predecessor | Resource Required | Databse
1 | <Release x.x> Code Freeze | [5 empty] | <Lead Engineer x> | Framework
2 | (Unit, Functional) Test Completion | <n> days |  |  |  |  | <Developer x> | BI tool
3 | Unit testing by developer | 1 Day | 2010-09-14 | 2010-09-15 | 80% |  | <Developer x> | Log In system
4 | Rework and fix any issues found by developers | <n> days |  |  |  | 2, 3 | <Lead Engineer x> | Request supplies
5 | Unit test reverification by developers | <n> days |  |  |  | 4 | <Developer x> | Forms
6 | Engineering Test Completetion sign-off | <n> days |  |  |  | 5 | <Lead Engineer x> | List of supplies
7 | Deploy Code to QA test server | <n> days |  |  |  | 5 | <Lead Engineer x>
8 | Create Change Request Form for Release and send to the Change Advisor board for reaview and approval | <n> days |  |  |  |  | <Release Coordinator x>
9 | Official start of QA Testing <Release x.x> | <n> days |  |  |  | 7 | <QA Manager x>
10 | Create Fix testing scripts <Release x.x> | <n> days |  |  |  |  | <QA Engineers x>
11 | Start Fix testing <Release x.x> | <n> days |  |  |  | 7, 10 | <QA Tester x>
12 | Rework and fixes any issues found by QA Tester as documented in defect tracking application | <n> days |  |  |  | 11
13 | Reverification of fixed issues by QA Tester | <n> days |  |  |  | 12
14 | Send Fix testing Status sign-off | <n> days |  |  |  | 13 | <QA Manager x>
15 | Regression testing <Release x.x> | <n> days |  |  |  | 14 | <QA Tester x>
16 | Rework and fixes any issues found by QA Tester as documented in defect tracking application | <n> days |  |  |  | 15
17 | Reverification of fixed issues by QA Tester | <n> days |  |  |  | 16
18 | Restart and complete regression testing to QA tester | <n> days |  |  |  | 17
19 | Send Regression testing Status sign-off | <n> days |  |  |  | 18 | <QA Manager x>
20 | Release Communication to Application clients | <n> days |  |  |  | 14, 19 | <Release Manager x>
21 | Complete and send Help/User Guide Documents update sign-off | <n> days |  |  |  | 14, 19 | <Technical Writer x>
22 | Deploy <Release x.x> Code and User Guide to PRODUCTION | <n> days |  |  |  | 14, 19, 20, 21 | <Deployment Coordinator x>
23 | Post Production Verification of <release x.x> | <n> days |  |  |  | 22 | <Implementation team x>