## Sheet1
Quality Assurance Testing Timeline for <Release x.x>
This timeline document is intended to serve as a alist of tasks needed to be accomplished during the Quality Assurance testing phase for a showing the duration of each task in the format <n> days, the start and finish in the format <nn/dd/yyyy>, the predecessors for the task and resource/s for the task to be successfuly completed.
Task ID | Task Name | Duration | Start | Finish | % Complete | Predecessor | Resource Required | Databse
1 | Evaluate current process of client |  | 2017-01-17 | 2017-01-17 | 100% |  |  | Framework
2 | Identify possible solutions | 1 day | 2017-01-17 | 2017-01-17 | 100% |  |  | BI tool
3 | Identify system process | 1 day | 2017-01-17 | 2017-01-17 | 100% | 1, 2 |  | Log In system
4 | Propose project | 1 day | 2017-01-20 | 2017-01-20 | 100% | 3 |  | Request supplies
5 | Project Management Plan | 1 day | 2017-02-02 | 2017-02-02 | 100% | 4 |  | Forms
6 | Quality Assurance Plan |  | 2017-02-09 | --- | 20%
7 | WBS | 1 day | 2017-02-10 | 2017-02-10 | 100% |  |  | List of supplies
8 | Gantt Chart | 1 day | 2017-02-10 | 2017-02-11 | 100% | 7
9 | Event Table | 1 day | 2017-02-14 | 2017-02-14 | 100% | 3
10 | Use Case Diagram | 1 day | 2017-02-15 | 2017-02-15 |  | 9
11 | Activity Diagram | 1 day | 2017-02-16 | 2017-02-16 | 100% | 9
12 | Context Flow Diagram | 1 day | 2017-02-15 | 2017-02-15 | 100% | 9
13 | Data Flow Diagram | 2 days | 2017-02-16 | 2017-02-17 | 100% | 9, 10, 11
14 | Entity Relationship Diagram | 2 days | 2017-02-18 | 2017-02-20 | 80% | 9 , 10, 11, 12, 13
15 | Database | 3 days | 2017-02-21 | 2017-02-24 |  | 14
16 | Business Intelligence Tool | 3 days | 2017-02-25 | 2017-02-28 |  | 15
17 | Login/Register Interface | 1 day | 2017-03-02 | 2017-03-02 |  | 15, 16
18 | LGU basic information form | 1 day | 2017-03-02 | 2017-03-02
19 | Advisory form | 1 day | 2017-03-04 | 2017-03-04 |  | 18
20 | Request supply form | 1 day | 2017-03-04 | 2017-03-04 |  | 19
21 | Historical data form | 1 day | 2017-03-06 | 2017-03-06 |  | 20
22 | List of accounts grid view | 1 day | 2017-03-07 | 2017-03-07 |  | 21
23 | List of requests grid view | 1 day | 2017-03-07 | 2017-03-07 |  | 22
24 | Working database | 2 days | 2017-03-09 | 2017-03-11 |  | 15
25 | Add and update data | 2 days | 2017-03-13 | 2017-03-14 |  | 24
26 | Working Business Intelligence tool | 2 days | 2017-03-16 | 2017-03-18 |  | 16
27 | Complete proof of concept for system

## Sheet2
1 | Project charter approved
Project plan completed
Project plan approved
Project team assembled
Project execution initiated
Project execution completed
Customer acceptance
Project closed out