## Sheet1
Quality Assurance Testing Timeline for <Release x.x>
This timeline document is intended to serve as a alist of tasks needed to be accomplished during the Quality Assurance testing phase for a showing the duration of each task in the format <n> days, the start and finish in the format <nn/dd/yyyy>, the predecessors for the task and resource/s for the task to be successfuly completed.
Task ID | Task Name | Duration | Start | Finish | % Complete | Predecessor | Resource Required | Databse
1 | Evaluate current process of client | [5 empty] | <Lead Engineer x> | Framework
2 | Identify possible solutions | <n> days |  |  |  |  | <Developer x> | BI tool
3 | Identify system process | 1 Day | 2010-09-14 | 2010-09-15 | 80% |  | <Developer x> | Log In system
4 | Propose project | <n> days |  |  |  | 2, 3 | <Lead Engineer x> | Request supplies
5 | Create Project Management Plan | <n> days |  |  |  | 4 | <Developer x> | Forms
6 | Create WBS | <n> days |  |  |  | 5 | <Lead Engineer x> | List of supplies
7 | Gantt Chart | <n> days |  |  |  | 5 | <Lead Engineer x>
8 | Event Table | <n> days |  |  |  |  | <Release Coordinator x>
9 | Use Case Diagram | <n> days |  |  |  | 7 | <QA Manager x>
10 | Activity Diagram | <n> days |  |  |  |  | <QA Engineers x>
11 | Context Flow Diagram | <n> days |  |  |  | 7, 10 | <QA Tester x>
12 | Data Flow Diagram | <n> days |  |  |  | 11
13 | Entity Relationship Diagram | <n> days |  |  |  | 12
14 | Business Intelligence Tool | <n> days |  |  |  | 13 | <QA Manager x>
15 | Database | <n> days |  |  |  | 14 | <QA Tester x>
16 | Login/Register Interface | <n> days |  |  |  | 15
17 | LGU basic information form | <n> days |  |  |  | 16
18 | Advisory form | <n> days |  |  |  | 17
19 | Request supply form | <n> days |  |  |  | 18 | <QA Manager x>
20 | Historical data form | <n> days |  |  |  | 14, 19 | <Release Manager x>
21 | List of accounts grid view | <n> days |  |  |  | 14, 19 | <Technical Writer x>
22 | List of requests grid view | <n> days |  |  |  | 14, 19, 20, 21 | <Deployment Coordinator x>
23 | Working database | <n> days |  |  |  | 22 | <Implementation team x>
Add and update data
Working Business Intelligence tool
Complete proof of concept for system

## Sheet2
1 | Project charter approved
Project plan completed
Project plan approved
Project team assembled
Project execution initiated
Project execution completed
Customer acceptance
Project closed out