## Sheet1
Activity # | Activity Name | Activity Name Description | # of Days | Start Date | Dependency | Milestone
| Initiating |  | 15 days
1 |  | Create Project Team | 0.5 days | 2017-01-16 |  | Create Project Team
2 |  | Discuss for the Possible Project | 3 days | 2017-01-16 |  | Discuss for the Possible Project
3 |  | Prepare Document for Adviser Request | 0.5 days | 2017-01-19 |  | Project Adviser Rrequest
4 |  | Project Initial Scope | 2.5 days | 2017-01-24 | 4 | Initial Scope of the Project
5 |  | Create Project Charter | 4 days | 2017-02-02 | 6 | Project Charter
| Planning |  | 12.5 days
6 |  | Define Project Scope | 1 day | 2017-02-10 | 4,6 | Scope of the Project
7 |  | Create WBS | 1 day | 2017-02-11 08:00 |  | Work Breakdown Structure
8 |  | Project Schedule | 0.5 days | 2017-02-13 | 10 | Project Schedule
9 |  | Human Resource Plan | 1 day | 2017-02-15 |  | Staffing Plan
10 |  | Communication Plan | 1 day | 2017-02-23 01:00 | 12 | Communication Planning
11 |  | Quality Assurance Strategy | 1 day | 2017-02-21 | 9,13 | Quality Assurance Strategy
12 |  | Risk Management Planning | 1 day | 2017-02-23 |  | Risk Management Planning
13 |  | Budget Estimate Cost | 0.5 days | 2017-02-23 |  | Budget Estimate Cost
14 |  | Procurement Management Plan | 0.5 days | 2017-02-24 |  | Procurement Management Plan
| Executing |  | 33.5 days
15 |  | Gantt Chart | 1 day | 2017-02-13 | 10 | Gantt Chart
16 |  | Event Table | 2 days | 2017-02-14 | 9 | Event Table
17 |  | Activity Diagram | 0.5 days | 2017-02-17 08:00 | 20 | Activity Diagram
18 |  | Context Flow Diagram | 1.5 days | 2017-02-17 08:00 | 20,21 | Context Flow Diagram
19 |  | Data Flow Diagram | 2 days | 2017-02-17 08:00 | 20,21,22 | Data Flow Diagram
20 |  | Database Design | 2.5 days | 2017-02-21 | 20,21,22,23 | Database Design
21 |  | System User Interface | 2 days | 2017-02-21 08:00 | 20,21,22,23,24 | System Design Interface
22 |  | Change in Scope | 1.5 days | 2017-02-28 | 20,21,22,23,24,25 | Change Request
23 |  | Analyze New System Process | 4.5 days | 2017-03-01 08:00 | 20,21,22,23,24,25,26 | Analyze New System Process
24 |  | Implement Business Intelligence Tool | 10.5 days | 2017-03-08 | 20,21,22,23,24,25,26,27 | Implement Business Intelligence Tool
25 |  | Datawarehousing Process | 3.5 days | 2017-03-14 | 24,27,28 | Datawarehousing Process
26 |  | User Web Application Design | 4.5 days | 2017-03-14 | 27,28 | User Web Application Design
27 |  | Quality Assurance Progress Review | 2.5 days | 2017-03-21 | 26,27,28,29,30 | Quality Assurance Progress Review
28 |  | Procurement Decision Criteria | 4 days | 2017-03-27 08:00 | 28,29 | Procurement Decision Criteria
| Monitoring and Controlling |  | 5 days
29 |  | Tools and Techniques for Assuring Quality | 1 day | 2017-03-03 08:00 |  | Tools and Techniques for Assuring Quality
30 |  | Testing | 1 day | 2017-03-06 08:00 | 34 | Quality Testing
31 |  | Validated Changes | 1 day | 2017-03-07 08:00 | 35 | Validated Changes
32 |  | Project Document Updates | 1.5 days | 2017-03-08 01:00 | 36 | Project Document Updates
| Closing |  | 16.5 days
33 |  | Audit Procurement | 1 day | 2017-03-14 01:00 | 32 | Audit Procurement
34 |  | Review Project Documents | 0.5 days | 2017-04-03 08:00 | 37 | Review Project Documents
35 |  | Update Project Files | 1 day | 2017-04-03 08:00 | 40 | Update Project Files
36 |  | Final Project Report | 1 day | 2017-04-05 08:00 | 41 | Final Project Report