## Sheet1
Level | WBS Code | Element Name | Description of Work
1 | 1 | NDRRMC Monitoring System | The work done for NDRRMC Monitoring System
2 | 1.1 | Initiation | The work done to start the project
3 | 1.1.1 | Create Project Team | Create Project Team
4 | 1.1.1.1 | Project Adviser, Manager, Team Member | Project Stakeholders
3 | 1.1.2 | Discuss Possible Project | Project team meeting
3 | 1.1.3 | Project Initial Scope | Project team define initial scope of the project
3 | 1.1.4 | Project Charter | Project team creates project charter
2 | 1.2 | Planning | Work for the planning process of the project
3 | 1.2.1 | Define Project Scope | Project team define project scope
3 | 1.2.2 | Create WBS | Create Work Breakdown Structure
3 | 1.2.3 | Project Schedule | Create Project Schedule
4 | 1.2.3.1 | Check Time Availability | Meeting with the team
4 | 1.2.3.2 | Estimate Project Duration | Meeting with the team
4 | 1.2.3.3 | Know Project Deadlines | Set deadlines for each work phase
3 | 1.2.4 | Human Resource Plan | Project Manager creates human resource plan
4 | 1.2.4.1 | Staffing Plan | Project Manager creates Staffing Plan
4 | 1.2.4.2 | Responsibility Matrices | Create responsibility matrices
3 | 1.2.5 | Communication Plan | Create Communication Plan
4 | 1.2.5.1 | Communication Management Approach | Create Communication Management Approach
4 | 1.2.5.2 | Project Team Directory | Create Project Team Directory
4 | 1.2.5.3 | Communication Matrix | Create Communication Matrix
3 | 1.2.6 | Quality Assurance Strategy | Project Manager creates QA Strategy
3 | 1.2.7 | Risk Management Plan | Project Manager creates Risk Management Plan
3 | 1.2.8 | Budget Estimate Cost | Create budget estimate cost of the project
3 | 1.2.9 | Procurement Management Plan | Create Procurement Plan
4 | 1.2.9.1 | Procurement Management Approach | Create Procurement Management Approach
2 | 1.3 | Executing | Work for executing process
3 | 1.3.1 | Gantt Chart | Create Gantt Chart
3 | 1.3.2 | Event Table | Project Team creates event table of the proposed project
3 | 1.3.3 | System Diagrams
3 | 1.3.3.1 | Activity Diagram | Assigned member creates activity diagram
3 | 1.3.3.2 | Context Flow Diagram | Assigned member creates context flow diagram
3 | 1.3.3.3 | Data Flow Diagram | Assigned member creates data flow diagram
3 | 1.3.4 | Database Design | Project team creates database design
3 | 1.3.5 | System User Interface | Project team creates system user interface
3 | 1.3.6 | Change in Scope | Project team define change in scope of the project
4 | 1.3.6.1 | Analyze New System Process | Project team define analyze new system process
4 | 1.3.6.2 | Implement Business Intelligence Tool | Project team study and implement BI Tool
4 | 1.3.6.3 | Datawarehousing Process | Project team study and implement the process of data warehousing
3 | 1.3.7 | User Web Application Design | Project team outline the design of the system
3 | 1.3.8 | Quality Assurance Progress Review | Quality Assurance Progress Review
3 | 1.3.9 | Procurement Decision Criteria | Creates procurement decision criteria
2 | 1.4 | Monitoring and Controlling | Work for monitoring and controlling process of the project
3 | 1.4.1 | Tools and Techniques for Assuring Quality | Define tools and techniques for assuring the quality of the project
3 | 1.4.2 | Testing | Testing of each system work phase
3 | 1.4.3 | Validated Changes | Project Manager validate changes in the project
3 | 1.4.4 | Project Document Updates | Project team update documents
2 | 1.5 | Closing | Work for closing process of the project
3 | 1.5.1 | Audit Procurement | Review and assess procuremet
3 | 1.5.2 | Review Project Documents | Review project documents
3 | 1.5.3 | Update Project Files | Update changes if any
3 | 1.5.4 | Final Project Report | Final project report