## Sheet1
Milestone | Milestone Goals | Due Date
Define Project Scope and Requirements | The project team should denfine the project scope and requirements for the completion of the proposed system | February 11,2017
Delegation of Tasks | Each member of the project team will be given a task for the completion of project requirements | February 13,2017
Define Hardware and Software needed for the project | Project team defines hardware and software needed for the development of the proposed system | 2017-02-24
System Design | System designs should fully implement to the system, it should be approved by the project team and suitable for input into the development code | 2017-03-20
Implement proposed Business Intelligence Tool | Impementaion of the BI Tool is needed for checking if the features and function suitable to the system | 2017-03-22
Testing Complete | Testing of all product features and function | 2017-04-04
Document Complete | Document such as Project Management Plan is reviewed by the project adviser | 2017-04-05